## ProjectSchedule
Track a Trace
Team 17 | Project Start: | 2022-09-19
| Today: | 2022-10-05
| Display Week: | 1 |  |  | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03
 | time axis 2022-09-19 to 2023-04-09
TASK | PROGRESS | START | END | DAYS | time axis 2022-09-19 to 2023-04-09
Design Phase
Problem Statement | 100% | 2022-09-19 | 2022-09-26 | 8
Development Plan | 100% | 2022-09-19 | 2022-09-26 | 8
Requirements Specification | 100% | 2022-09-27 | 2022-10-05 | 9
Hazard Analysis | 0% | 2022-10-06 | 2022-10-19 | 14
Verification and Validation Plan | 0% | 2022-10-20 | 2022-11-02 | 14
POC Demonstration | 0% | 2022-11-03 | 2022-11-14 | 12
Design Specification | 0% | 2022-12-18 | 2023-01-18 | 32
Coding Phase
Understanding GERT source code | 10% | 2022-09-23 | 2023-01-18 | 118
Revision 0 Demonstration | 0% | 2023-01-19 | 2023-02-06 | 19
Verification and Validation Report | 0% | 2023-02-07 | 2023-03-08 | 30
Final Phase
Final Demonstration | 0% | 2023-03-01 | 2023-03-20 | 20
Final Documentation | 0% | 2023-03-21 | 2023-04-05 | 16
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.